## ProductBackLog
Project Name:Monitoring and Assistance System for At-Home Physiotherapy Exercises Group Members:Dilara KETİ,Arda ABACI,Batuhan DELİARSLAN,Can GÜRÇAY,İkbal ELMAS,Kerem GÜLER,Cafer Kaan COŞKUN
# | Product BackLog
1 | Design scalable tables for users, sessions, and sensors.
2 | Implement Bcrypt-based registration and login system.
3 | Setup AES-256 for health records and video streams.
4 | Deploy pose algorithm with 90% tracking accuracy.
5 | Link live feed to the motion analysis engine.
6 | Define mathematical benchmarks for correct movements.
7 | Build logic to identify posture and angle deviations.
8 | Design high-contrast interface for elderly users.
9 | Integrate professional exercise guidance videos.
10 | Add customized 3D figures for movement demonstration.
11 | Implement red/green on-screen status indicators.
12 | Add real-time audio instructions for corrections.
13 | Establish Bluetooth link with the vital sign band.
14 | Record heart rate and physiological metrics in real-time.
15 | Build auto-save to resume sessions after crashes.
16 | Create a dashboard for remote clinician monitoring.
17 | Generate automated PDF/CSV performance summaries.
18 | Identify patient-specific mobility limitations.
19 | Full localization for Turkish and English.
20 | Ensure 99.9% uptime and 2-second latency.

## Sprint-1
SPRINT-1
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer, Product Owner | Database Schema Design | In Progress | High | 2028-09-04 | 2028-09-08 | 5 | Creating the core structure for patients and exercises.
Developer | User Registration & Roles | Ready to Start | High | 2028-09-08 | 2028-09-13 | 6 | Setting up the 3-minute registration flow for all users.
Developer | AES-256 Encryption | Ready to Start | Medium | 2028-09-13 | 2028-09-17 | 5 | Securing the environment for sensitive health data.
Developer | Accessibility UI Framework | Ready to Start | Low | 2028-09-17 | 2028-09-21 | 5 | Building the elderly-friendly visual layout.
21
BACKLOG
As a user, I want to register securely within 3 minutes so that I can start using the application immediately.
STATUS: Ready to Start
As an admin, I want all patient data to be encrypted with AES-256 so that we ensure KVKK compliance.
STATUS: Ready to Start
A.H
V.O

## Sprint-2
SPRINT-2
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | YOLO Pose Setup | Not Started | High | 2028-09-21 | 2028-09-28 | 8 | Deploying the motion tracking algorithm with 90% accuracy.
Developer | Pre-recorded Video Library | Not Started | High | 2028-09-28 | 2028-09-30 | 3 | Populating the app with exercise content.
Developer | 3D Figure Presentation | Not Started | Medium | 2028-09-30 | 2028-10-03 | 5 | Finalizing 3D visual aids for patient guidance.
Developer | Real-Time Camera Analysis | Not Started | Medium | 2028-10-03 | 2028-10-07 | 5 | Linking the camera feed to the tracking system.
Developer | 2-Second Performance Optimization | Not Started | Low | 2028-10-07 | 2028-10-11 | 5 | Tuning the backend for low-latency results.
26
BACKLOG
As a patient, I want to see 3D figures demonstrating the movements so that I can perform them correctly.
STATUS: Not Started
As a patient, I want to see a skeleton overlay on my own camera view so that I can align my body parts correctly with the target pose.
STATUS: Not Started
İ.B
As a user, I want the motion analysis to be accurate and fast so that I don't wait for results during exercise.
STATUS: Not Started
U.R
L.E

## Sprint-3
SPRINT-3
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | Sensor Band Synchronization | Not Started | High | 2028-10-11 | 2028-10-16 | 6 | Connecting wearable sensors via Bluetooth.
Developer | Physiological Data Logging | Not Started | High | 2028-10-16 | 2028-10-20 | 5 | Recording heart rate and vitals to database.
Developer | Incorrect Movement Logic | Not Started | Medium | 2028-10-20 | 2028-10-27 | 8 | Defining rules for posture/angle deviations.
Developer | Real-time Audio-Visual Feedback | Not Started | Medium | 2028-10-27 | 2028-11-01 | 6 | Real-time alerts for movement corrections.
Developer | Search & Filter Functionality | Not Started | Low | 2028-11-01 | 2028-11-04 | 4 | Filtering historical session data for user.
29
BACKLOG
As a patient, I want to be alerted immediately when I make a wrong move to prevent injury.
STATUS: Not Started
As a patient, I want to be alerted immediately when I make a wrong move to prevent injury.
STATUS: Not Started
E.T
G.H

## Sprint-4
SPRINT-4
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | Physical Limitation Detection | Not Started | High | 2028-11-04 | 2028-11-08 | 5 | Identifying patient-specific movement issues.
Developer | Second Optimization | Not Started | High | 2028-11-08 | 2028-11-13 | 6 | Reducing system latency after full integration.
Developer | Physiotherapist Dashboard | Not Started | Medium | 2028-11-13 | 2028-11-18 | 6 | Generating clinical reports and summaries.
Developer | Multi-Language Localization | Not Started | Medium | 2028-11-18 | 2028-11-21 | 4 | Finalizing Turkish and English localization.
Developer | Stability & Final QA Tests | Not Started | Low | 2028-11-21 | 2028-11-26 | 6 | End-to-end stress testing and bug fixing.
27
BACKLOG
As a physiotherapist, I want to see detailed reports of my patients so that I can track their recovery.
STATUS: Not Started
As a user, I want to use the application in my native language so that I can understand all instructions.
STATUS: Not Started
B.C
A.S
As a physiotherapist, I want to filter patients who are struggling with specific exercises so that I can provide them with extra support.
STATUS: Not Started
F.D

## KeyDropdowns
PRIORITY KEY | STATUS KEY
High | In Progress
Medium | Ready to Start
Low | Complete
On Hold
Testing
Not Started

## Templates
TEMPLATES
ASSIGNED TO | KANBAN CARDS
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
As a physiotherapist, I want detailed reports to track recovery. (STATUS: Not Started)
As a patient, I want to be alerted immediately for wrong moves. (STATUS: Not Started)
As a user, I want the app to resume my session after a crash. (STATUS: To Do)
As a user, I want to use the app in my native language easily. (STATUS: To Do)
As a patient, I want to see 3D figures so I can perform moves correctly. (STATUS: Not Started)
As a physiotherapist, I want to filter struggling patients for support. (STATUS: To Do)